## projects
project_id | bu | department | project_name | start_date | due_date | status | priority
P001 | Components | Analyzer Delivery | Aftermarket Analyzer Upgrade | 2026-01-03 | 2026-02-15 | Completed | High
P002 | Manufacturing | Analyzer Delivery | Manufacturing Diagnostics Rollout | 2026-01-10 | 2026-03-05 | Completed | High
P003 | Digital | Analytics | Telematics KPI Automation | 2026-02-01 | 2026-03-28 | Completed | Medium
P004 | Quality | Project Engineering | Plant Quality Data Cleanup | 2026-02-12 | 2026-04-12 | Completed | Medium

## tasks
task_id | project_id | engineer | department | bu | task_type | assigned_date | due_date | completion_date | status
T001 | P001 | Asha | Analyzer Delivery | Components | Requirements | 2026-01-05 | 2026-01-14 | 2026-01-13 | Completed
T002 | P001 | Asha | Analyzer Delivery | Components | Configuration | 2026-01-15 | 2026-01-29 | 2026-01-30 | Completed
T003 | P001 | Ishita | Analytics | Components | Testing | 2026-01-30 | 2026-02-12 | 2026-02-10 | Completed
T004 | P002 | Rohan | Analyzer Delivery | Manufacturing | Data Mapping | 2026-01-18 | 2026-02-05 | 2026-02-06 | Completed
T005 | P002 | Asha | Analyzer Delivery | Manufacturing | Automation | 2026-02-06 | 2026-02-18 | 2026-02-21 | Completed
T006 | P002 | Rohan | Analyzer Delivery | Manufacturing | Go-Live Support | 2026-02-19 | 2026-03-04 | 2026-03-03 | Completed
T007 | P003 | Ishita | Analytics | Digital | KPI Design | 2026-02-03 | 2026-02-20 | 2026-02-18 | Completed
T008 | P003 | Pranav | Automation | Digital | Excel Integration | 2026-02-21 | 2026-03-05 | 2026-03-05 | Completed
T009 | P003 | Rohan | Analyzer Delivery | Digital | UAT Support | 2026-03-06 | 2026-03-24 | 2026-03-22 | Completed
T010 | P004 | Nina | Quality | Quality | Data Audit | 2026-02-15 | 2026-03-12 | 2026-03-11 | Completed
T011 | P004 | Vikram | Project Engineering | Quality | Cleanup Rules | 2026-03-13 | 2026-03-29 | 2026-03-29 | Completed
T012 | P004 | Vikram | Project Engineering | Quality | Validation Dashboard | 2026-03-30 | 2026-04-10 | 2026-04-10 | Completed

## performance
task_id | rft | otd | rework_count | delay_reason
T001 | 1 | 1 | 0
T002 | 1 | 0 | 0 | Configuration approval delay
T003 | 0 | 1 | 1
T004 | 1 | 0 | 0 | Source data clarification
T005 | 0 | 0 | 2 | Late scope change
T006 | 1 | 1 | 0
T007 | 1 | 1 | 0
T008 | 1 | 1 | 0
T009 | 1 | 1 | 0
T010 | 0 | 1 | 1
T011 | 1 | 1 | 0
T012 | 1 | 1 | 0

## feedback
task_id | rating | comments | date
T003 | 4.6 | Strong collaboration and quick turnaround. | 2026-02-11
T005 | 4.1 | Needed tighter scope control. | 2026-02-22
T008 | 4.8 | Automation significantly improved reporting quality. | 2026-03-06
T012 | 4.3 | Solid execution with clear validation evidence. | 2026-04-11

## skill_matrix
engineer | department | skill | category | rating
Asha | Analyzer Delivery | Analyzer Configuration | Technical | 4.7
Asha | Analyzer Delivery | Excel Automation | Tools | 4.5
Asha | Analyzer Delivery | Stakeholder Management | Project | 4.4
Asha | Analyzer Delivery | Cummins Domain | Business | 4.2
Rohan | Analyzer Delivery | SQL Diagnostics | Technical | 4.1
Rohan | Analyzer Delivery | Power Query | Tools | 4.6
Rohan | Analyzer Delivery | Delivery Coordination | Project | 4
Rohan | Analyzer Delivery | Manufacturing Process | Business | 3.9
Ishita | Analytics | Python Analytics | Technical | 4.8
Ishita | Analytics | Power BI Modeling | Tools | 4.4
Ishita | Analytics | Quality Planning | Project | 4.5
Ishita | Analytics | Telematics | Business | 4.1
Vikram | Project Engineering | Root Cause Analysis | Technical | 4
Vikram | Project Engineering | Project Planner | Tools | 3.8
Vikram | Project Engineering | Execution Control | Project | 4.2
Vikram | Project Engineering | Plant Operations | Business | 3.9
Nina | Quality | Validation Testing | Technical | 4.2
Nina | Quality | Quality Checklists | Tools | 4.1
Nina | Quality | Issue Escalation | Project | 3.9
Nina | Quality | Quality Systems | Business | 4
Pranav | Automation | Power Automate | Technical | 4.4
Pranav | Automation | Excel Macros | Tools | 4.5
Pranav | Automation | Release Readiness | Project | 4.1
Pranav | Automation | Reporting Operations | Business | 3.8

## engineer_master
engineer | department | availability_pct
Asha | Analyzer Delivery | 78
Rohan | Analyzer Delivery | 82
Ishita | Analytics | 90
Vikram | Project Engineering | 94
Nina | Quality | 72
Pranav | Automation | 55