## projects
project_id | bu | department | project_name | start_date | due_date | status | priority
P001 | Components | Analyzer Delivery | Aftermarket Analyzer Upgrade | 2026-01-03 | 2026-02-15 | Completed | High
P002 | Manufacturing | Analyzer Delivery | Manufacturing Diagnostics Rollout | 2026-01-10 | 2026-03-05 | Completed | High
P003 | Digital | Analytics | Telematics KPI Automation | 2026-02-01 | 2026-03-28 | Completed | Medium
P004 | Quality | Project Engineering | Plant Quality Data Cleanup | 2026-02-12 | 2026-04-12 | Completed | Medium

## tasks
task_id | project_id | engineer | department | bu | task_type | assigned_date | due_date | completion_date | status | schedule_variance_days
T001 | P001 | Asha | Analyzer Delivery | Components | Requirements | 2026-01-05 | 2026-01-14 | 2026-01-13 | Completed | -1
T002 | P001 | Asha | Analyzer Delivery | Components | Configuration | 2026-01-15 | 2026-01-29 | 2026-01-30 | Completed | 1
T003 | P001 | Ishita | Analytics | Components | Testing | 2026-01-30 | 2026-02-12 | 2026-02-10 | Completed | -2
T004 | P002 | Rohan | Analyzer Delivery | Manufacturing | Data Mapping | 2026-01-18 | 2026-02-05 | 2026-02-06 | Completed | 1
T005 | P002 | Asha | Analyzer Delivery | Manufacturing | Automation | 2026-02-06 | 2026-02-18 | 2026-02-21 | Completed | 3
T006 | P002 | Rohan | Analyzer Delivery | Manufacturing | Go-Live Support | 2026-02-19 | 2026-03-04 | 2026-03-03 | Completed | -1
T007 | P003 | Ishita | Analytics | Digital | KPI Design | 2026-02-03 | 2026-02-20 | 2026-02-18 | Completed | -2
T008 | P003 | Pranav | Automation | Digital | Excel Integration | 2026-02-21 | 2026-03-05 | 2026-03-05 | Completed | 0
T009 | P003 | Rohan | Analyzer Delivery | Digital | UAT Support | 2026-03-06 | 2026-03-24 | 2026-03-22 | Completed | -2
T010 | P004 | Nina | Quality | Quality | Data Audit | 2026-02-15 | 2026-03-12 | 2026-03-11 | Completed | -1
T011 | P004 | Vikram | Project Engineering | Quality | Cleanup Rules | 2026-03-13 | 2026-03-29 | 2026-03-29 | Completed | 0
T012 | P004 | Vikram | Project Engineering | Quality | Validation Dashboard | 2026-03-30 | 2026-04-10 | 2026-04-10 | Completed | 0

## performance
task_id | rft | otd | rework_count | delay_reason
T001 | 1 | 1 | 0
T002 | 1 | 0 | 0 | Configuration approval delay
T003 | 0 | 1 | 1
T004 | 1 | 0 | 0 | Source data clarification
T005 | 0 | 0 | 2 | Late scope change
T006 | 1 | 1 | 0
T007 | 1 | 1 | 0
T008 | 1 | 1 | 0
T009 | 1 | 1 | 0
T010 | 0 | 1 | 1
T011 | 1 | 1 | 0
T012 | 1 | 1 | 0

## feedback
task_id | rating | comments | date
T003 | 4.6 | Strong collaboration and quick turnaround. | 2026-02-11
T005 | 4.1 | Needed tighter scope control. | 2026-02-22
T008 | 4.8 | Automation significantly improved reporting quality. | 2026-03-06
T012 | 4.3 | Solid execution with clear validation evidence. | 2026-04-11

## skill_matrix
engineer | department | skill | category | rating
Asha | Analyzer Delivery | Analyzer Configuration | Technical | 4.7
Asha | Analyzer Delivery | Excel Automation | Tools | 4.5
Asha | Analyzer Delivery | Stakeholder Management | Project | 4.4
Asha | Analyzer Delivery | Cummins Domain | Business | 4.2
Rohan | Analyzer Delivery | SQL Diagnostics | Technical | 4.1
Rohan | Analyzer Delivery | Power Query | Tools | 4.6
Rohan | Analyzer Delivery | Delivery Coordination | Project | 4
Rohan | Analyzer Delivery | Manufacturing Process | Business | 3.9
Ishita | Analytics | Python Analytics | Technical | 4.8
Ishita | Analytics | Power BI Modeling | Tools | 4.4
Ishita | Analytics | Quality Planning | Project | 4.5
Ishita | Analytics | Telematics | Business | 4.1
Vikram | Project Engineering | Root Cause Analysis | Technical | 4
Vikram | Project Engineering | Project Planner | Tools | 3.8
Vikram | Project Engineering | Execution Control | Project | 4.2
Vikram | Project Engineering | Plant Operations | Business | 3.9
Nina | Quality | Validation Testing | Technical | 4.2
Nina | Quality | Quality Checklists | Tools | 4.1
Nina | Quality | Issue Escalation | Project | 3.9
Nina | Quality | Quality Systems | Business | 4
Pranav | Automation | Power Automate | Technical | 4.4
Pranav | Automation | Excel Macros | Tools | 4.5
Pranav | Automation | Release Readiness | Project | 4.1
Pranav | Automation | Reporting Operations | Business | 3.8

## engineer_master
engineer | department | availability_pct
Asha | Analyzer Delivery | 78
Rohan | Analyzer Delivery | 82
Ishita | Analytics | 90
Vikram | Project Engineering | 94
Nina | Quality | 72
Pranav | Automation | 55

## project_kpis
project_id | bu | department | project_name | start_date | due_date | status | priority | total_tasks | completed_tasks | rft | otd | avg_rework_count | feedback_score | feedback_count | project_health
P001 | Components | Analyzer Delivery | Aftermarket Analyzer Upgrade | 2026-01-03 | 2026-02-15 | Completed | High | 3 | 3 | 0.66667 | 0.66667 | 0.33333 | 4.6 | 1 | Red
P002 | Manufacturing | Analyzer Delivery | Manufacturing Diagnostics Rollout | 2026-01-10 | 2026-03-05 | Completed | High | 3 | 3 | 0.66667 | 0.33333 | 0.66667 | 4.1 | 1 | Red
P003 | Digital | Analytics | Telematics KPI Automation | 2026-02-01 | 2026-03-28 | Completed | Medium | 3 | 3 | 1 | 1 | 0 | 4.8 | 1 | Green
P004 | Quality | Project Engineering | Plant Quality Data Cleanup | 2026-02-12 | 2026-04-12 | Completed | Medium | 3 | 3 | 0.66667 | 1 | 0.33333 | 4.3 | 1 | Amber

## utilization
engineer | department | availability_pct | assigned_tasks | completed_tasks | overdue_tasks | workload_pct | utilization_pct | billable_utilization_pct | utilization_band | allocation_flag
Asha | Analyzer Delivery | 78 | 3 | 3 | 2 | 134.62 | 100 | 100 | High | Overloaded
Rohan | Analyzer Delivery | 82 | 3 | 3 | 1 | 128.05 | 100 | 100 | High | Overloaded
Ishita | Analytics | 90 | 2 | 2 | 0 | 77.78 | 77.78 | 77.78 | Optimal | Balanced
Vikram | Project Engineering | 94 | 2 | 2 | 0 | 74.47 | 74.47 | 74.47 | Optimal | Balanced
Pranav | Automation | 55 | 1 | 1 | 0 | 63.64 | 63.64 | 63.64 | Low | Balanced
Nina | Quality | 72 | 1 | 1 | 0 | 48.61 | 48.61 | 48.61 | Bench | Underutilized

## capability_scores
engineer | department | capability_score | categories_covered | avg_rating | capability_band
Ishita | Analytics | 4.54 | 4 | 4.45 | Expert
Asha | Analyzer Delivery | 4.51 | 4 | 4.45 | Expert
Pranav | Automation | 4.255 | 4 | 4.2 | Advanced
Rohan | Analyzer Delivery | 4.145 | 4 | 4.15 | Advanced
Nina | Quality | 4.075 | 4 | 4.05 | Advanced
Vikram | Project Engineering | 3.995 | 4 | 3.975 | Advanced

## skill_breakdown
engineer | department | category | rating | weight | weighted_score
Asha | Analyzer Delivery | Business | 4.2 | 0.15 | 0.63
Asha | Analyzer Delivery | Project | 4.4 | 0.25 | 1.1
Asha | Analyzer Delivery | Technical | 4.7 | 0.4 | 1.88
Asha | Analyzer Delivery | Tools | 4.5 | 0.2 | 0.9
Ishita | Analytics | Business | 4.1 | 0.15 | 0.615
Ishita | Analytics | Project | 4.5 | 0.25 | 1.125
Ishita | Analytics | Technical | 4.8 | 0.4 | 1.92
Ishita | Analytics | Tools | 4.4 | 0.2 | 0.88
Nina | Quality | Business | 4 | 0.15 | 0.6
Nina | Quality | Project | 3.9 | 0.25 | 0.975
Nina | Quality | Technical | 4.2 | 0.4 | 1.68
Nina | Quality | Tools | 4.1 | 0.2 | 0.82
Pranav | Automation | Business | 3.8 | 0.15 | 0.57
Pranav | Automation | Project | 4.1 | 0.25 | 1.025
Pranav | Automation | Technical | 4.4 | 0.4 | 1.76
Pranav | Automation | Tools | 4.5 | 0.2 | 0.9
Rohan | Analyzer Delivery | Business | 3.9 | 0.15 | 0.585
Rohan | Analyzer Delivery | Project | 4 | 0.25 | 1
Rohan | Analyzer Delivery | Technical | 4.1 | 0.4 | 1.64
Rohan | Analyzer Delivery | Tools | 4.6 | 0.2 | 0.92
Vikram | Project Engineering | Business | 3.9 | 0.15 | 0.585
Vikram | Project Engineering | Project | 4.2 | 0.25 | 1.05
Vikram | Project Engineering | Technical | 4 | 0.4 | 1.6
Vikram | Project Engineering | Tools | 3.8 | 0.2 | 0.76

## power_bi_dataset
task_id | project_id | engineer | department_task | bu_task | task_type | assigned_date | due_date_task | completion_date | status_task | schedule_variance_days | bu_project | department_project | project_name | start_date | due_date_project | status_project | priority | rft | otd | rework_count | delay_reason | feedback_rating | feedback_comments | feedback_date | bu | department | project_name_project_kpi | start_date_project_kpi | due_date | status | priority_project_kpi | total_tasks | completed_tasks_x | rft_project_kpi | otd_project_kpi | avg_rework_count | feedback_score | feedback_count | project_health | availability_pct | assigned_tasks | completed_tasks_y | overdue_tasks | workload_pct | utilization_pct | billable_utilization_pct | utilization_band | allocation_flag | capability_score | categories_covered | avg_rating | capability_band | avg_feedback_score | rft_pct | otd_pct | portfolio_utilization_pct | portfolio_workload_pct | portfolio_capability_score
T001 | P001 | Asha | Analyzer Delivery | Components | Requirements | 2026-01-05 | 2026-01-14 | 2026-01-13 | Completed | -1 | Components | Analyzer Delivery | Aftermarket Analyzer Upgrade | 2026-01-03 | 2026-02-15 | Completed | High | 1 | 1 | 0 |  | 0 |  |  | Components | Analyzer Delivery | Aftermarket Analyzer Upgrade | 2026-01-03 | 2026-02-15 | Completed | High | 3 | 3 | 0.66667 | 0.66667 | 0.33333 | 4.6 | 1 | Red | 78 | 3 | 3 | 2 | 134.62 | 100 | 100 | High | Overloaded | 4.51 | 4 | 4.45 | Expert | 4.6 | 100 | 100 | 77.42 | 87.86 | 4.25
T002 | P001 | Asha | Analyzer Delivery | Components | Configuration | 2026-01-15 | 2026-01-29 | 2026-01-30 | Completed | 1 | Components | Analyzer Delivery | Aftermarket Analyzer Upgrade | 2026-01-03 | 2026-02-15 | Completed | High | 1 | 0 | 0 | Configuration approval delay | 0 |  |  | Components | Analyzer Delivery | Aftermarket Analyzer Upgrade | 2026-01-03 | 2026-02-15 | Completed | High | 3 | 3 | 0.66667 | 0.66667 | 0.33333 | 4.6 | 1 | Red | 78 | 3 | 3 | 2 | 134.62 | 100 | 100 | High | Overloaded | 4.51 | 4 | 4.45 | Expert | 4.6 | 100 | 0 | 77.42 | 87.86 | 4.25
T003 | P001 | Ishita | Analytics | Components | Testing | 2026-01-30 | 2026-02-12 | 2026-02-10 | Completed | -2 | Components | Analyzer Delivery | Aftermarket Analyzer Upgrade | 2026-01-03 | 2026-02-15 | Completed | High | 0 | 1 | 1 |  | 4.6 | Strong collaboration and quick turnaround. | 2026-02-11 | Components | Analyzer Delivery | Aftermarket Analyzer Upgrade | 2026-01-03 | 2026-02-15 | Completed | High | 3 | 3 | 0.66667 | 0.66667 | 0.33333 | 4.6 | 1 | Red |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 4.6 | 0 | 100 | 77.42 | 87.86 | 4.25
T004 | P002 | Rohan | Analyzer Delivery | Manufacturing | Data Mapping | 2026-01-18 | 2026-02-05 | 2026-02-06 | Completed | 1 | Manufacturing | Analyzer Delivery | Manufacturing Diagnostics Rollout | 2026-01-10 | 2026-03-05 | Completed | High | 1 | 0 | 0 | Source data clarification | 0 |  |  | Manufacturing | Analyzer Delivery | Manufacturing Diagnostics Rollout | 2026-01-10 | 2026-03-05 | Completed | High | 3 | 3 | 0.66667 | 0.33333 | 0.66667 | 4.1 | 1 | Red | 82 | 3 | 3 | 1 | 128.05 | 100 | 100 | High | Overloaded | 4.145 | 4 | 4.15 | Advanced | 4.1 | 100 | 0 | 77.42 | 87.86 | 4.25
T005 | P002 | Asha | Analyzer Delivery | Manufacturing | Automation | 2026-02-06 | 2026-02-18 | 2026-02-21 | Completed | 3 | Manufacturing | Analyzer Delivery | Manufacturing Diagnostics Rollout | 2026-01-10 | 2026-03-05 | Completed | High | 0 | 0 | 2 | Late scope change | 4.1 | Needed tighter scope control. | 2026-02-22 | Manufacturing | Analyzer Delivery | Manufacturing Diagnostics Rollout | 2026-01-10 | 2026-03-05 | Completed | High | 3 | 3 | 0.66667 | 0.33333 | 0.66667 | 4.1 | 1 | Red | 78 | 3 | 3 | 2 | 134.62 | 100 | 100 | High | Overloaded | 4.51 | 4 | 4.45 | Expert | 4.1 | 0 | 0 | 77.42 | 87.86 | 4.25
T006 | P002 | Rohan | Analyzer Delivery | Manufacturing | Go-Live Support | 2026-02-19 | 2026-03-04 | 2026-03-03 | Completed | -1 | Manufacturing | Analyzer Delivery | Manufacturing Diagnostics Rollout | 2026-01-10 | 2026-03-05 | Completed | High | 1 | 1 | 0 |  | 0 |  |  | Manufacturing | Analyzer Delivery | Manufacturing Diagnostics Rollout | 2026-01-10 | 2026-03-05 | Completed | High | 3 | 3 | 0.66667 | 0.33333 | 0.66667 | 4.1 | 1 | Red | 82 | 3 | 3 | 1 | 128.05 | 100 | 100 | High | Overloaded | 4.145 | 4 | 4.15 | Advanced | 4.1 | 100 | 100 | 77.42 | 87.86 | 4.25
T007 | P003 | Ishita | Analytics | Digital | KPI Design | 2026-02-03 | 2026-02-20 | 2026-02-18 | Completed | -2 | Digital | Analytics | Telematics KPI Automation | 2026-02-01 | 2026-03-28 | Completed | Medium | 1 | 1 | 0 |  | 0 |  |  | Digital | Analytics | Telematics KPI Automation | 2026-02-01 | 2026-03-28 | Completed | Medium | 3 | 3 | 1 | 1 | 0 | 4.8 | 1 | Green | 90 | 2 | 2 | 0 | 77.78 | 77.78 | 77.78 | Optimal | Balanced | 4.54 | 4 | 4.45 | Expert | 4.8 | 100 | 100 | 77.42 | 87.86 | 4.25
T008 | P003 | Pranav | Automation | Digital | Excel Integration | 2026-02-21 | 2026-03-05 | 2026-03-05 | Completed | 0 | Digital | Analytics | Telematics KPI Automation | 2026-02-01 | 2026-03-28 | Completed | Medium | 1 | 1 | 0 |  | 4.8 | Automation significantly improved reporting quality. | 2026-03-06 | Digital | Analytics | Telematics KPI Automation | 2026-02-01 | 2026-03-28 | Completed | Medium | 3 | 3 | 1 | 1 | 0 | 4.8 | 1 | Green |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 4.8 | 100 | 100 | 77.42 | 87.86 | 4.25
T009 | P003 | Rohan | Analyzer Delivery | Digital | UAT Support | 2026-03-06 | 2026-03-24 | 2026-03-22 | Completed | -2 | Digital | Analytics | Telematics KPI Automation | 2026-02-01 | 2026-03-28 | Completed | Medium | 1 | 1 | 0 |  | 0 |  |  | Digital | Analytics | Telematics KPI Automation | 2026-02-01 | 2026-03-28 | Completed | Medium | 3 | 3 | 1 | 1 | 0 | 4.8 | 1 | Green |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 4.8 | 100 | 100 | 77.42 | 87.86 | 4.25
T010 | P004 | Nina | Quality | Quality | Data Audit | 2026-02-15 | 2026-03-12 | 2026-03-11 | Completed | -1 | Quality | Project Engineering | Plant Quality Data Cleanup | 2026-02-12 | 2026-04-12 | Completed | Medium | 0 | 1 | 1 |  | 0 |  |  | Quality | Project Engineering | Plant Quality Data Cleanup | 2026-02-12 | 2026-04-12 | Completed | Medium | 3 | 3 | 0.66667 | 1 | 0.33333 | 4.3 | 1 | Amber |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 4.3 | 0 | 100 | 77.42 | 87.86 | 4.25
T011 | P004 | Vikram | Project Engineering | Quality | Cleanup Rules | 2026-03-13 | 2026-03-29 | 2026-03-29 | Completed | 0 | Quality | Project Engineering | Plant Quality Data Cleanup | 2026-02-12 | 2026-04-12 | Completed | Medium | 1 | 1 | 0 |  | 0 |  |  | Quality | Project Engineering | Plant Quality Data Cleanup | 2026-02-12 | 2026-04-12 | Completed | Medium | 3 | 3 | 0.66667 | 1 | 0.33333 | 4.3 | 1 | Amber | 94 | 2 | 2 | 0 | 74.47 | 74.47 | 74.47 | Optimal | Balanced | 3.995 | 4 | 3.975 | Advanced | 4.3 | 100 | 100 | 77.42 | 87.86 | 4.25
T012 | P004 | Vikram | Project Engineering | Quality | Validation Dashboard | 2026-03-30 | 2026-04-10 | 2026-04-10 | Completed | 0 | Quality | Project Engineering | Plant Quality Data Cleanup | 2026-02-12 | 2026-04-12 | Completed | Medium | 1 | 1 | 0 |  | 4.3 | Solid execution with clear validation evidence. | 2026-04-11 | Quality | Project Engineering | Plant Quality Data Cleanup | 2026-02-12 | 2026-04-12 | Completed | Medium | 3 | 3 | 0.66667 | 1 | 0.33333 | 4.3 | 1 | Amber | 94 | 2 | 2 | 0 | 74.47 | 74.47 | 74.47 | Optimal | Balanced | 3.995 | 4 | 3.975 | Advanced | 4.3 | 100 | 100 | 77.42 | 87.86 | 4.25

## department_performance
department | projects_tracked | engineers_tracked | tasks_tracked | rft_pct | otd_pct | avg_feedback_score | avg_capability_score | avg_workload_pct
Analytics | 1 | 3 | 3 | 100 | 100 | 4.8 | 1.5133 | 25.9267
Analyzer Delivery | 2 | 3 | 6 | 66.6667 | 50 | 4.35 | 3.6367 | 109.9933
Project Engineering | 1 | 2 | 3 | 66.6667 | 100 | 4.3 | 2.6633 | 49.6467

## engineer_performance
engineer | department | assigned_projects | assigned_tasks | rft_pct | otd_pct | avg_feedback_score | capability_score | workload_pct | allocation_flag
Ishita | Analytics | 1 | 1 | 100 | 100 | 0 | 4.54 | 77.78 | Balanced
Vikram | Project Engineering | 1 | 2 | 100 | 100 | 2.15 | 3.995 | 74.47 | Balanced
Asha | Analyzer Delivery | 2 | 3 | 66.6667 | 33.3333 | 1.3667 | 4.51 | 134.62 | Overloaded
Rohan | Analyzer Delivery | 1 | 2 | 100 | 50 | 0 | 4.145 | 128.05 | Overloaded
Ishita | Analyzer Delivery | 1 | 1 | 0 | 100 | 4.6 | 0 | 0
Nina | Project Engineering | 1 | 1 | 0 | 100 | 0 | 0 | 0
Pranav | Analytics | 1 | 1 | 100 | 100 | 4.8 | 0 | 0
Rohan | Analytics | 1 | 1 | 100 | 100 | 0 | 0 | 0